## Slide 1
10G Ethernet-to-LA1224 PCIe Datapath Driver Development
KYOCERA Weekly Report April 22, 2026

## Slide 2
Kyocera – Datapath Driver Weekly Status Report
Apr | Project Week 04
Overall Summary
Completed SDK and DPDK familiarization including DPAA2 PMD, la12xx bbdev PMD, and NIC binding via VFIO.
Completed Build Environment setup: 1 GB hugepages reserved, DPRC bound to vfio-fsl-mc, testpmd verified at 10 Gbps link speed with 825M packets TX at zero errors.
Completed EAL and Port Init application: builds cleanly against DPDK 19.11-qoriq, initializes EAL, configures DPAA2 port, creates mempool, sets up RX/TX queues, and runs a 30-second RX poll loop.
First RX capture result: 86 packets received over 30 seconds (36,025 bytes), zero errors and zero drops. Week 4 foundation for DPDK application development is complete.
Next (WW05): bbdev Init (la12xx PMD, IPC handshake), RX Path (rte_eth_rx_burst, bbdev op prep).
Tessolve Semiconductors | Kyocera SLD Laser | Confidential

## Slide 3
Kyocera – Datapath Driver Weekly Status Report
Apr | Project Week 04
WW 04
Module | Component | Description | Status | Test Status | ETA | Remarks
SDK / DPDK Study | DPDK APIs | DPAA2 PMD, la12xx bbdev, NIC binding study | Completed | PASS | 18-Apr | Team ready for development
Build Environment | Hugepage / VFIO / DPRC | 1 GB hugepage, DPRC bound, testpmd verified | Completed | PASS | 21-Apr | testpmd: 825M pkts TX, 0 errors
EAL + Port Init | kyocera_pmd_init (DPAA2 PMD) | EAL init, port config, mempool, RX/TX queues, 30s poll | Completed | PASS | 22-Apr | 86 pkts RX, 0 errors, 0 drops
WW 05
Module | Component | Description | Status | Test Status | ETA | Remarks
bbdev Init | la12xx BBdev PMD | bbdev device init, queue pair, IPC handshake | Not Started |  | 26-Apr | Open /dev/gulipc0, IPC rings up
RX Path | DPAA2 PMD + bbdev prep | rte_eth_rx_burst, payload extract, bbdev op prep | Not Started |  | 28-Apr | Extend polling loop in kyocera_pmd_init
bbdev Enqueue | la12xx BBdev PMD | rte_bbdev_enqueue_enc_ops with hugepage phys addr | Not Started |  | 29-Apr | LDPC params per BW, graceful drop on full
Tessolve Semiconductors | Kyocera SLD Laser | Confidential
Backlog
Module | Component | Description | Status | Test Status | ETA | Remarks
- | - | - | - |  | - | No blockers
Module | Component | Description | Status | Test Status | ETA | Remarks
bbdev Init | la12xx BBdev PMD | bbdev device init, queue pair setup, IPC handshake (HOST_MEM_READY / IPC_LIB_READY to FECA_READY) | Not Started |  | 26-Apr | Open /dev/gulipc0, IPC rings live
RX Path | DPAA2 PMD + bbdev prep | rte_eth_rx_burst, payload extraction, bbdev raw op preparation with hugepage phys addr | Not Started |  | 28-Apr | Extend polling loop in kyocera_pmd_init

## Slide 4
Action Items – Weekly Status
S.No | Action Item | Status | Remarks
1 | UDP Test | Completed | Single stream - 5.00 Gbps Single stream (max) - 5.20 Gbps Multi stream RX - 5.00 Gbps Multi stream TX - 4.10 Gbps Bidirectional - 8.49 Gbps Multi instance (4X2G) - 8.00 Gbps Multi instance (3x2.25G) - 6.75 Gbps All tests passed with zero packet loss.
4 | SW architecture document V0.3 | Completed | Added pipeline approach on the burst size adaption in a detailed flow chart.

## Slide 5
Task 1: SDK and DPDK Study
Objective:
Understand DPDK APIs, DPAA2 PMD, and la12xx bbdev PMD before writing driver code.
Scope of Study:
• DPDK 19.11-qoriq (NXP LSDK 2004 build)
• DPAA2 net PMD architecture and VFIO binding model
• bbdev framework APIs (rte_bbdev_enqueue_enc_ops / rte_bbdev_dequeue_dec_ops)
• Hugepage memory model and mbuf mempool management
Method:
• Reviewed DPDK 19.11 programmer's guide and source tree
• Studied pre-built static libraries under /usr/local/lib/librte_*.a
• Mapped the datapath flow: NIC -> DPAA2 PMD -> mbuf -> bbdev -> LA1224
Topic | Coverage
DPDK Build Model | Static libs, selective linking
DPAA2 PMD | DPRC, fslmc bus, vfio-fsl-mc
bbdev Framework | Enqueue / Dequeue / MSI
Conclusion:
SDK study complete. Team aligned on the architecture and APIs before hands-on coding.
Tessolve Semiconductors | Kyocera SLD Laser | Confidential

## Slide 6
Task 2: Build Environment Setup
Objective:
Prepare the LX2160A so DPDK can take ownership of the DPAA2 10G Ethernet port.
Method:
• Reserved 1 GB hugepages (2 x 1 GB)
• Created DPRC container (dprc.2) and bound it to vfio-fsl-mc
• Verified with dpdk-testpmd: probe + TX sanity test
Check | Result
1 GB Hugepages | 2 x 1 GB allocated
DPRC vfio bind | vfio-fsl-mc
testpmd probe | Link UP 10 Gbps
testpmd TX sanity | 825M pkts, 0 errors
Key Insight:
DPDK successfully takes the NIC away from the kernel and drives it at packet rate line speed.
Conclusion:
Build environment validated. DPDK owns the 10G NIC and is ready for application development.
Tessolve Semiconductors | Kyocera SLD Laser | Confidential

## Slide 7
Task 3: EAL and Port Init Application
Objective:
Build and validate the first skeleton DPDK application (kyocera_pmd_init) that initializes EAL, configures the DPAA2 port, creates a mempool, and runs an RX poll loop.
Method:
• Wrote main.c with EAL init, port config, mempool create, RX/TX queue setup
• Built with custom Makefile (selective PMD linking, no pkg-config)
• Ran 30-second RX poll loop on the 10G DPAA2 port
Metric | Result
EAL Init | OK (16 lcores, VFIO)
Port Config | OK (net_dpaa2)
RX mbufs in 30 s | 86
Errors / Drops | 0 / 0
Key Insight:
• 4 build issues resolved: missing libdpdk.pc, OpenSSL symbol errors, missing dpaax_iova_table, Makefile tab/whitespace.
• 86 packets received confirm the RX pipeline is live end to end.
Conclusion:
Foundation for the DPDK driver is complete. Ready for bbdev integration in
Week 05.
Tessolve Semiconductors | Kyocera SLD Laser | Confidential

## Slide 8
Results at a Glance
Task | Validates | Key Numbers | Result
Task 1 | SDK / DPDK Study | DPAA2 PMD, bbdev APIs, VFIO binding model reviewed | PASSED
Task 2 | Build Environment (Hugepages + VFIO + testpmd) | 1 GB hugepages, dprc.2 bound 825M pkts TX, 0 errors | PASSED
Task 3 | EAL + Port Init (kyocera_pmd_init) | Builds clean, runs, 86 pkts RX, 0 errors, 0 drops | PASSED
Tessolve Semiconductors | Kyocera SLD Laser | Confidential

## Slide 9
Performance Targets
• ≥ 8 Gbps throughput
• < 200 μs p99 latency
• < 0.001% loss
• Variable bandwidth (100-720 MHz)
10G Ethernet Network
Upstream/Downstream Traffic
RX
TX
LX2160A Host (Linux + DPDK Datapath)
WRIOP/DPAA2
QBMAN
DDR/Mempools
CPU Cores
bbdev: LDPC Enc/Dec • BG1/BG2 • z_c • Code Rate • RV • CRC • Bandwidth: 100-720 MHz
ops+DMA
writeback
PCIe Gen3 x8
~8 GB/s bandwidth
encode/decode
results
LA1224 LDPC Accelerator (FECA)
Multi-queue encode/decode • CRC check • Variable bandwidth (100-720 MHz)
Flowchart

## Slide 10
Thank You
Parthiban Balan
parthiban.pavadaibalan@tessolve.com
+91 88847 34443