## Slide 1
10G Ethernet-to-LA1224 PCIe Datapath Driver Development
KYOCERA Weekly Report April 29, 2026

## Slide 2
Kyocera – Datapath Driver Weekly Status Report
Apr | Project Week 05
Overall Summary
Completed Task 1: bbdev device initialization on la12xx PMD; queues configured (LDPC_ENC, LDPC_DEC); IPC handshake with LA1224 firmware completed.
Completed Task 2: RX path with Kyocera test packet filter; allocated bbdev op pool (2048); 5000 packets received and 5000 ops prepared with zero drops.
Built setup_state.sh automation: full state reset (yami reload, PCIe re-enumeration, /dev/gulipc nodes, DPRC vfio bind) in one command.
Validated platform on DPDK 22.11.4 (NXP LSDK 2108). Resolved 4 transitions: kernel module device-name match, PCI map exhaust, VFIO group lock, dynamic /dev major detection.
Next (WW06): LDPC Enqueue Parameter Understanding and bbdev Enqueue Implementation
Tessolve Semiconductors | Kyocera SLD Laser | Confidential

## Slide 3
Kyocera – Datapath Driver Weekly Status Report
Apr | Project Week 05
WW 05
Module | Component | Description | Status | Test Status | ETA | Remarks
bbdev Init | la12xx BBdev PMD | bbdev device init, queue pair, IPC handshake | Completed | PASS | 24-Apr | baseband_la12xx probed, FECA ready
RX Path | DPAA2 PMD + bbdev op pool | rte_eth_rx_burst, filter, op alloc | Completed | PASS | 28-Apr | 5000 pkts, 5000 ops, 0 drops
Automation | setup_state.sh | yami reset, PCIe re-enum, /dev nodes, DPRC bind | Completed | PASS | 28-Apr | Auto-detect gulipc major
WW 06
Module | Component | Description | Status | Test Status | ETA | Remarks
bbdev Enqueue | la12xx BBdev PMD | rte_bbdev_enqueue_enc_ops with hugepage zero-copy | Not Started |  | 5-May | LDPC params per BW, drop on full
bbdev Dequeue | la12xx BBdev PMD | rte_bbdev_dequeue_dec_ops + CRC validation | Not Started |  | 7-May | MSI/eventfd completion
TX Path | DPAA2 PMD | rte_eth_tx_burst, hugepage buffer, no memcpy | Not Started |  | 9-May | Zero-copy egress to 10G NIC
Tessolve Semiconductors | Kyocera SLD Laser | Confidential
Backlog
Module | Component | Description | Status | Test Status | ETA | Remarks
- | - | - | - | - | - | No blockers
Module | Component | Description | Status | Test Status | ETA | Remarks
LDPC Enqueue Parameter Understanding | LDPC param study + Kyocera alignment | Study LDPC params (BG, z_c, q_m, CB mode, RV, CRC, output size); confirm per-BW with Kyocera; document defaults. | Not Started |  | 02-May | -
bbdev Enqueue Implementation | la12xx BBdev PMD + main.c | Alloc output mbuf pool, fill op fields, call rte_bbdev_enqueue_enc_ops, track enq counters, add dequeue drain; test the throughput. | Not Started |  | 05-May | -

## Slide 4
Action Items - Weekly Status
S.No | Action Item | Status | Remarks
1 | Task 1: bbdev device init + queue config + IPC handshake | Completed | baseband_la12xx PMD, FECA ready
2 | Task 2: RX path with packet filter and bbdev op pool | Completed | 5000 pkts received, 5000 ops, 0 drops
3 | Build setup_state.sh automation script | Completed | Full reset in one command

## Slide 5
Task 1: bbdev Device Initialization
Objective:
Initialize the LA1224 baseband device via la12xx BBdev PMD, set up two queues (encode + decode), and complete the IPC handshake.
Scope:
rte_bbdev_count and probe via RTE_BBDEV_FOREACH
rte_bbdev_setup_queues for 2 queue allocation
rte_bbdev_queue_configure (LDPC_ENC and LDPC_DEC, queue_size=16)
rte_bbdev_start performs the IPC handshake (host writes ready flags, modem responds FECA_READY)
Method:
Add bbdev includes to main.c (rte_bbdev.h, rte_bbdev_op.h)
Update Makefile to use pkg-config libdpdk + ALLOW_EXPERIMENTAL_API
Coordinate with LA1224 UART: type 'test bbdev_ipc1 0x3f 1' before host start
Step | Result
bbdev probe | 1 device, baseband_la12xx
Queue configuration | q0=LDPC_ENC, q1=LDPC_DEC
IPC handshake | FECA_READY received
Conclusion:
bbdev pipeline is operational. LA1224 FECA is ready to accept LDPC operations from the host.
Tessolve Semiconductors | Kyocera SLD Laser | Confidential

## Slide 6
Task 2: RX Path with bbdev Op Preparation
Objective:
Receive Ethernet frames from the 10G NIC, filter Kyocera test packets, and allocate one bbdev op per matching packet (no enqueue yet, that is Task 3).
Method:
• Reserved 1 GB hugepages (2 x 1 GB)
• Created DPRC container (dprc.2) and bound it to vfio-fsl-mc
• Verified with dpdk-testpmd: probe + TX sanity test
Metric | Result
Packets sent | 5000
rx_test (filter) | 5000
ops_prepared | 5000
op_alloc_drops | 0
Key Insight:
DPDK successfully takes the NIC away from the kernel and drives it at packet rate line speed.
Conclusion:
Build environment validated. DPDK owns the 10G NIC and is ready for application development.
Tessolve Semiconductors | Kyocera SLD Laser | Confidential

## Slide 7
Next Steps: Week 06 Plan
Goal:
Understand LDPC Enqueue Parameter the Complete the enqueue LDPC ops to LA1224
Tasks:
Task 1 : Understand the LDPC Enqueue Parameters.
Task 2 (5-May): rte_bbdev_enqueue_enc_ops with LDPC params (BG, z_c, code rate) and zero-copy hugepage payload
Task | Target
LDPC understanding | 5-May
bbdev Enqueue | 9-May
Key Insight:
The two completed tasks build the foundation; Task 1 is the first real cross-PCIe data movement.
LDPC parameter set will come from Kyocera (BG1/BG2, z_c, code rate per bandwidth).
Conclusion:
Foundation complete.
Tessolve Semiconductors | Kyocera SLD Laser | Confidential

## Slide 8
Results at a Glance
Task | Validates | Key Numbers | Result
Task 1 | bbdev Init (la12xx PMD) | 1 device probed, 2 queues, IPC handshake OK | PASSED
Task 2 | RX Path + packet filter | 5000 sent, 5000 rx_test, 5000 ops, 0 drops | PASSED
Task 3 | Automation (setup_state.sh) | yami + PCIe + DPRC + /dev in one command | DELIVERED
Tessolve Semiconductors | Kyocera SLD Laser | Confidential

## Slide 9
Performance Targets
• ≥ 8 Gbps throughput
• < 200 μs p99 latency
• < 0.001% loss
• Variable bandwidth (100-720 MHz)
10G Ethernet Network
Upstream/Downstream Traffic
RX
TX
LX2160A Host (Linux + DPDK Datapath)
WRIOP/DPAA2
QBMAN
DDR/Mempools
CPU Cores
bbdev: LDPC Enc/Dec • BG1/BG2 • z_c • Code Rate • RV • CRC • Bandwidth: 100-720 MHz
ops+DMA
writeback
PCIe Gen3 x8
~8 GB/s bandwidth
encode/decode
results
LA1224 LDPC Accelerator (FECA)
Multi-queue encode/decode • CRC check • Variable bandwidth (100-720 MHz)
Flowchart

## Slide 10
Thank You
Parthiban Balan
parthiban.pavadaibalan@tessolve.com
+91 88847 34443