## Slide 1
10G Ethernet-to-LA1224 PCIe Datapath Driver Development
KYOCERA Weekly Report April 08, 2026

## Slide 2
Kyocera – Datapath Driver Weekly Status Report
Apr | Project Week 02
Overall Summary
1. Received LA1224-RDB eval board. Board boot, serial (LA1224) and SSH (LX2160A) access verified.
2. FR2 analog loopback completed: 400 MHz OFDM TX (CORRECT), RX captured, SINAD measured (50.8 dB Ch5, 22.3 dB Ch4).
We were able to successfully generate and receive OFDM packets using the FR1/FR2 Test Tool.
Booted VSPA images (2T2R, 400 MHz, 1966 Msps) and started all HS DCS channels — both TX and RX running in FDD mode
Generated TM3.1 OFDM waveforms at 400 MHz bandwidth on HSDAC0 and HSDAC1 — TX data verified CORRECT on both channels
Captured RX data through SMA coaxial loopback (DAC→cable→ADC) on the FR2 breakout board
Measured SINAD at 400 MHz single tone:
  50.8 dB on Channel 5
  22.3 dB on Channel 4 .
8. The board, PCIe Gen3 x8 link, yami driver, IPC handshake, and all 8 VSPA cores are confirmed working.
9. Next week: 10G Ethernet iperf baseline, dpdk-test-bbdev LDPC loopback, PCIe IPC benchmark.
Tessolve Semiconductors | Kyocera SLD Laser | Confidential

## Slide 3
Kyocera – Datapath Driver Weekly Status Report
Apr | Project Week 2
WW 02
Module | Component | Description | Status | Test Status | ETA | Remarks
Board Bring-Up | LX2160A + LA1224 | Boot, SSH, Serial | Completed | PASS | 6-Apr | Linux 5.15 RT, PCIe x8, IPC ready
FR2 Loopback Test | HS DCS / VSPA | OFDM TX/RX, SINAD | Completed | PASS | 8-Apr | SINAD: 50.8 dB (Ch5), 22.3 dB (Ch4)
WW 03
Module | Component | Description | Status | Test Status | ETA | Remarks
10G Ethernet | DPAA2 / WRIOP | iperf baseline | Not Started |  | 13-Apr | -
dpdk-test-bbdev | BBdev / la12xx PMD | LDPC enc/dec loopback | Not Started |  | 15-Apr | -
IPC Benchmark | BBdev RAW | PCIe throughput baseline | Not Started |  | 15-Apr | -
Backlog
Module | Component | Description | Status | Test Status | ETA | Remarks
- | - | - | - |  | - | No blockers.
Tessolve Semiconductors | Kyocera SLD Laser | Confidential

## Slide 4
Performance Targets
• ≥ 8 Gbps throughput
• < 200 μs p99 latency
• < 0.001% loss
• Variable bandwidth (100-720 MHz)
10G Ethernet Network
Upstream/Downstream Traffic
RX
TX
LX2160A Host (Linux + DPDK Datapath)
WRIOP/DPAA2
QBMAN
DDR/Mempools
CPU Cores
bbdev: LDPC Enc/Dec • BG1/BG2 • z_c • Code Rate • RV • CRC • Bandwidth: 100-720 MHz
ops+DMA
writeback
PCIe Gen3 x8
~8 GB/s bandwidth
encode/decode
results
LA1224 LDPC Accelerator (FECA)
Multi-queue encode/decode • CRC check • Variable bandwidth (100-720 MHz)
Flowchart

## Slide 5
Thank You
Parthiban Balan
parthiban.pavadaibalan@tessolve.com
+91 88847 34443